## Sheet1
Design and build an Inventory system for a local grocery store.
| Create Preliminary Invstigation Report |  | Define Objects |  | Begin Pseudo Code for Objects
| Duration: 1 | assigned: Jeffrey | Duration: 1 | Assigned: Jeffrey | Duration: 2 | assigned: Jeffrey
| Start 02/25 | Complete: 02/25 | Start 02/26 | Complete: 02/26 | Start 02/27 | Complete: 03/01
| Code Objects |  | Integrate Objects
| Duration: 14 | Assigned: Jeffrey, Zachary | Duration: 2 | Assigned: Jeffrey, Zachary
| Start: 03/02 | Complete: 03/16 | Start: 03/17 | Complete 03/19
| Create Documentation |  | Code Cleanup and Formatting |  | Final Project Submission
| Duartion: 2 | Assigned: Kenyon | Duration: 1 | Assigned: Jeffrey and Zachary | Duration: 1 | Jeffrey, Zachary, Kenyon
| Start: 03/17 | Complete: 03/19 | Start: 03/20 | Complete: 03/20 |  | Complete: 04/25