## Week 4 WBS Sheets
WBS
# | Task Name |  | Duration (days) | Predecessor
1 | Cost and benefit data |  | 3
2 | email town council- schedule |  | 1 | 1
3 | develop preposal |  | 5 | 1
4 | print handouts |  | 2 | 3
5 | Develop Powerpoint presentation |  | 5 | 3
6 | conduct rehersal |  | 2 | 5
7 | Deliver Presentation |  | 1 | 1,3,5, 6
PERT CPM
PERT CPM | [11 empty] | Rehershal
| Review Cost and benefit Data |  |  |  | PERT CPM |  |  | PERT CPM |  |  |  | Start Day: | ID:
| Start Day: 1 | ID: 1 |  |  |  | Email Town Council |  |  | Print handouts |  |  | Finish Day: | Dur:
| Finish Day: 3 | Dur: 3 |  |  |  | Start Day: 4 | ID: 2 |  | Start Day: 9 | ID: 4
[6 empty] | Finish Day: 4 | Dur: 1 |  | Finish Day: 10 | Dur: 2
PERT CPM
[6 empty] | Develop Preposal |  | PERT CPM | [6 empty] | PERT CPM
[6 empty] | Start Day: 4 | ID: 3 |  | Develop Powerpoint | [6 empty] | Deliver Presentation
[6 empty] | Finish Day: 8 | Dur: 5 |  | Start Day: 9 | ID: 5 | [5 empty] | Start Day: | ID:
[9 empty] | Finish Day: 13 | Dur: 5 | [5 empty] | Finish Day: | Dur:
WBS
# | Task Name |  | Duration (days) | Predecessor
1 | Meet with Manager |  | 5
2 | Interviews |  | 5 | 1
3 | Review Company Records |  | 3 | 2
4 | Observe Business Operations |  | 8 | 2
5 | Analyze Bumblebee software |  | 5 | 3,4
6 | Study sales & billing transactions |  | 2 | 3,4
7 | prepare report for Susan |  | 1
PERT CPM |  |  |  |  | PERT CPM |  |  | PERT CPM |  |  |  | PERT CPM
| Meet with Managers |  |  |  |  | Interviews |  |  | Observe Business Operations |  |  |  | Study Sales & Billing Trans.
| Start Day: 1 | ID: 1 |  |  |  | Start Day: 6 | ID#: 2 |  | Start Day: 11 | ID#: 4 |  |  | Start Day: 19 | ID#:6
| Finish Day: 5 | Dur: 5 |  |  |  | Finish Day: 10 | Dur: 5 |  | End day: 18 | Dur: 8 |  |  | End day: 20 | Dur: 2
PERT CPM
[6 empty] | Review Company Records |  | PERT CPM |  |  |  | PERT CPM
[6 empty] | Start Day: 11 | ID#:3 |  | Analyze Bumblebee Sofrware |  |  |  | Prepare Report For Susan
[6 empty] | End day:13 | Dur: 3 |  | Start Day: 19 | ID#: 5 |  |  | Start Day: 24 | ID#: 7
[9 empty] | End day:23 | Dur: 5 |  |  | End day: 24 | Dur: 1

## Sheet2
Gantt Sheet, Eden Bay
Cost and Benefit Data for Proposal
Email request for proposal on Agenda
Develop Proposal, including all necessary documents and charts